Trinidad ISD District Improvement Plan

2024-2025

# MISSION STATEMENT

Trinidad ISD will prepare all students for a successful future through education, encouragement, and expectations for excellence.

# VISION

Trinidad ISD will ensure the academic, social, and emotional success of each child with the positive influence of supportive loving professionals. The next generation will have a significant impact on society.

## VALUES

- We will define mastery for each grade level/course and assist each student in achieving mastery.

- We will ensure that all exiting students have a transitional plan.

- Administrators will stay current on educational research and issues.

- We will communicate instructional strategies, develop benchmarks, and practice cross-curricular instruction.

- We will model and expect high quality work.

- We will implement challenging student-centered activities and instruction.

- We will use effective classroom management to create a positive learning environment.

- We will monitor benchmark and survey results to identify student and district needs.

- We will encourage parent and community participation in creating a shared learning experience.

GOALS

Goal 1:

Trinidad’s PLC will increase student performance on all academic standards.

### Goal 2:

Trinidad’s PLC will create and maintain a positive learning environment.

Goal 3:

Trinidad’s PLC will improve communication with all district stakeholders.

# Trinidad ISD’s Goals Are Specific Measurable Attainable Results-Focused & Timely

| GOALS | S | M | A | R | T |
| --- | --- | --- | --- | --- | --- |
| All students in grades K-12 will improve performance on the STAAR reading or local literacy assessments for all students and a focus on accountable subpopulations. | Reading Literacy | Documented Increased Achievement on assessment results | Literacy Improvement | 5% all student groups 10% of accountable subpopulations Listening/Frustration… Instructional… Independent | By end of SY 2024-2025 |
| All students in grades K-12 will improve performance on the STAAR math or local assessment. | Math | Documented Increased Achievement on assessment results | Scores | 5% all student groups 10% of accountable subpopulations | By end of SY 2024-2025 |
| Students will learn in a safe & secure environment | Safety & Security | Documented Level of SCOC Violations, Projects, Clubs | Student Health & Safety | Students authentically engaged in their learning | Each 6 weeks |
| All students and teachers will have access to technology to lead to enhanced learning and best practices professional development | Technology Integration | Classroom equipment and internet access | Developing Technical Skills | Student and staff use of technology to enhance learning (grade level, college, career, certifications) | Throughout 2024-2025 SY |

| Strategies Resources |  |
| --- | --- |
| Pre-K/K Teacher CLI |  |
| M CLASS (BOY, MOY, EOY) Assessments K-2 |  |
| K-5 Amplify/MSC Zearn |  |
| Campus Level Review of Assessment Data by Subject – Texas Assessment |  |
| 1 – Safe/Security Education and equipment, Discipline, Assemblies, Book study, Bullying, Drug/Alcohol Abuse, Nutrition, Health Ed. |  |
| Provide computers/tablets, Wi-Fi access and/or software for every instructional classroom, and assist in college/career readiness through programs/technology | Computer Technician on campus |

THE STATE OF TEXAS PUBLIC EDUCATION MISSION AND ACADEMIC GOALS

The mission of the public education system of this state is to ensure that all Texas children have access to a quality education that enables them to achieve their potential and fully participate now and the future in the social, economic, and education opportunities of our state and nation.  That mission is grounded on the conviction that a general diffusion of knowledge is essential for the welfare of this state and for the preservation of the liberties and rights of citizens.  It is further grounded on the conviction that a successful public education system is directly related to a strong, dedicated, and supportive family; and that parental involvement in the school is essential for the maximum educational achievement of a child.

THE STATE OF TEXAS PUBLIC EDUCATION GOALS

GOAL #1:	The student in the public education system will demonstrate exemplary performance in the reading and writing of the 				English language.

GOAL #2:	The students in the public education system will demonstrate exemplary performance in the understanding of mathematics.

GOAL #3:	The students in the public education system will demonstrate exemplary performance in the understanding of science.

GOAL #4:	The students in the public education system will demonstrate exemplary performance in the understanding of social studies.

THE STATE OF TEXAS PUBLIC EDUCATION OBJECTIVES

Objective #1: Parents will be full partners with educators in the education of their children.

Objective #2: Students will be encouraged and challenged to meet their full educational potential.

Objective #3: Through enhanced dropout prevention efforts, all students will remain in school until they obtain a high school diploma.

Objective #4: A well-balanced and appropriate curriculum will be provided to all students.

Objective #5: Qualified and highly effective personnel will be recruited, developed, and retained.

Objective #6: The state’s students will demonstrate exemplary performance in the comparison to national and international standards.

Objective #7: School campuses will maintain a safe and disciplined environment conducive to student learning.

Objective #8: Educators will keep abreast of the development of creative and innovative techniques as appropriate to improve student learning.

Objective #9: Technology will be implemented and used to increase the effectiveness of student learning, instructional management, staff development, and administration.

# Comprehensive Needs Assessment Summary

# School Year: 2023-2024

| Data Sources Reviewed: - Current DIP, School Report Card including STAAR, Budget, SAT/ACT Statistics, College/Trade/Military Monitoring - Student/Staff/Community-Parent input from committees, List of Past School Events, Current Curriculum/Textbooks/Supplementary Aids - Elective Offerings, Progress Report & Report Card Grades, List of Available Technology & Uses, Professional Development Lists - Drills & Safety Data, Attendance Data |  |  |  |
| --- | --- | --- | --- |
| Area Reviewed | Summary of Strengths What were the identified strengths? | Summary of Needs What were the identified needs? | Priorities What are the priorities for the campus, including how federal and state program funds will be used? |
| Demographics | Diverse ethnic student population | Diverse ethnic educators | Recruit, and interview from diverse pools. State and local funds |
| Student Achievement | Results of STAAR, implantation of Strong Foundations Grant, accreditation continues to improve. | Improvement of comprehension, critical thinking, and problem solving | Employ Instructional Coaches – LASO Funds |
| School Culture and Climate | Diverse socioeconomic backgrounds | Social integration activities | Documented programs, assemblies, trips, etc. TIV PA and Local Funds |
| Staff Quality/ Professional Development | Admin. professional development aligns with district/campus needs | Professional development calendar for staff should align with TISD needs. | Assign professional development map to interventionist – (align with needs) TIPA, TII PA, TIV PA, and local funds |
| Curriculum, Instruction, Assessment | State adopted textbooks, some curriculum mapping, supplemental software | Vertical and Horizontal Alignment | Get curriculum aligned through campus/subject meetings and professional development. TIPA & TII PA and local funds |
| Family and Community Involvement | Parents are visible and financially supportive of athletic programs and UIL academics. | Establish an Educational Foundation geared toward academic improvement. | Identify community stakeholders and host meetings for discussion on beginning a grassroots program. Local time and funds. |
| School Context and Organization | TISD has been one of the most successful districts in the area recently. | Establish a public relations platform. | District commercial, Photography focus, Student media program SRSA and local funds |
| Technology | District website is accessible. Students and staff have devices. | Informational district website that speaks for us, introducing TISD | Digital maintenance of app and website. Local time and SRSA funds |

Title I, Part A

Schoolwide Components:

- A comprehensive needs assessment of the entire school (including taking into account the needs of migratory children as defined in section 1309(2)) that is based on information which includes the achievement of children in relation to the State academic content standards and the State student academic achievement standards described in section 1111(b)(1).

- Schoolwide reform strategies that  provide opportunities for all children to meet the State’s proficient and advanced levels of student academic achievement,  use effective methods and instructional strategies that are based on scientifically based research, and  that include strategies to address the needs of all children in the school, but particularly the needs of low-achieving children and those at risk of not meeting the State student academic achievement standards who are members of the target population of any program that is included in the schoolwide program.

- Instruction by highly qualified teachers.

- In accordance with section 1119 and subsection (a)(4), high-quality and ongoing professional development for teachers, principals, and paraprofessionals and, if appropriate, pupil services personnel, parents, and other staff to enable all children in the school to meet the State’s student academic achievement standards.

- Strategies to attract high-quality teachers to high-need schools.

- Strategies to increase parental involvement in accordance with section 1118, such as family literary services.

- Plans for assisting preschool children in the transition from early childhood programs, such as Head Start, Even Start, Early Reading First, or a State-run preschool program, to local elementary school programs.

- Measures to include teachers in the decisions regarding the use of academic assessments described in section 1111(b)(3) in order to provide information on, and to improve, the achievement of individual students and the overall instructional program.

- Activities to ensure that students who experience difficulty mastering the proficient or advanced levels of academic achievement standards required by section 1111(b) (1) shall be provided with effective, timely additional assistance which shall include measures to ensure that student difficulties are identified on a timely basis and to provide sufficient information on which to base effective assistance.

- Coordination and integration of Federal, State, and local services and programs, including programs supported under this Act, violence prevention programs, nutrition programs, housing programs, Head Start, adult education, vocational and technical education, and job training.

| Goal 1 Trinidad’s PLC will increase student performance on all academic standards. |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objective(s): |  |  |  |  |  |  |  |
| Value 1 & 8: We will assist each student in achieving mastery for each grade level course. |  |  |  |  |  |  |  |
| Strategies and Action Steps | Person(s) Responsible | Resources | Timelines | Evidence of Implementation | Evidence of Impact | Formative/ Summative | Title I Schoolwide Components (Code by #) |
| Review accountability data with all instructional staff | Michael Warren Kaylee Sims | NA | Completed by 10/07/2025 | In-service agenda | Feedback from district stakeholders | F=Meeting Agendas S=Annual Evaluation | 2 8 |
| Use of TEKS in structuring all lessons | Instructional Staff | District adopted materials | Aug. 2024- May 2025 | Lesson Plans | Benchmark and EOC | F=Lesson Plans S=Assessment Results | 3 |
| Schedule will be adjusted periodically for academic intervention. | Kaylee Sims Michael Warren | Master Schedule | Aug. 2024- May 2025 | Adjusted Schedule Calendar | Student Progress Report | F=Progress and Grade Reports S=Final STAAR | 9 |
| District wide curriculum alignment in core subject areas. | Kaylee Sims Michael Warren Laci Mizell Staff | Local Funds LASO Funds | Aug. 2024- May 2025 | Vertical/Horizontal alignment, TEKS, Assessments, Walkthroughs | Visual Monitoring and T-TESS | F=Alignment Map S=Assessment Scores/Ratings | 2 |

| Strategies and Action Steps | Person(s) Responsible | Resources | Timelines | Evidence of Implementation | Evidence of Impact | Formative/ Summative | Title I Schoolwide Components (Code by #) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Master schedules are revised to provide core content instruction to all students early in the day to minimize loss of instructional time due to extracurricular activities. | Michael Warren | None | Aug. 2024 | Master Schedule | Attendance records | F/S= Master Schedule | 2 |
| All students with history of retention or at-risk of retention, or failure of STAAR, EOC will be offered remediation/intervention | Kaylee Sims Michael Warren Instructional Staff | Compensatory Federal Funds Academic Software | Each grading period | Intervention schedules and lists | Academic progress reports | F= Progress reports S= TEKS mastery Charts | 2 |
| A minimum of one benchmark will be administered annually. Students not meeting standards will be placed in intervention. | Kaylee Sims Michael Warren Instructional Staff | Compensatory DMAC Software Federal Funds | Jan. 2025 | Benchmark documents | Needs Assessment document | F= Initial results S= Adjustments/Tracking Tutorial assignments | 1 2 4 |

| Ideal State: Goal(s) Goal 1 Trinidad’s PLC will increase student performance on all academic standards. |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objective(s)Value 2: We will ensure that all exiting students have a transitional plan, and that appropriate programs are implemented. |  |  |  |  |  |  |  |
| Strategies and Action Steps | Person(s) Responsible | Resources | Timelines | Evidence of Implementation | Evidence of Impact | Formative/ Summative | Title I Schoolwide Components |
| The District will update and keep 4 year plans current and yearly transcript review. | Michael Warren | None | By December 2024 Continually updated | Completed 4-year plans | Tracking documents (post-secondary) | F=Periodic Checks S=Completion of Activity | 6 10 |
| The District will implement endorsement programs. | Michael Warren Samantha Podlucky Natalie Martin Kaylee Sims | Local and Career Cruising (Perkins) | Aug 2024-June 2025 | Listed endorsement offerings | Student completed plans | F=Periodic Checks S=Completion of Activity | 3 6 10 |
| Post-Secondary prep. will be implemented through PSAT, SAT, ACT, TSI, ASVAB, etc. | Michael Warren Sponsors | General Fund | Aug 2024-June 2025 | Program and assessment offerings | Assessment participation and results | F=Participation Rates S=Registration/ Results | 8 10 |
| Dual Credit courses will be offered through qualified institutions | Kaylee Sims Michael Warren Matt Mizell | State Allotments | Aug 2024-July 2025 | MOUs and course offerings | Enrollment and grade results | F=Participation Rates S=Successful Completion | 2 3 |

| Ideal State: Goal(s) Goal 1 Trinidad’s PLC will increase student performance on all academic standards. |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objective(s)Value 2: We will ensure that all exiting students have a transitional plan, and that appropriate programs are implemented. |  |  |  |  |  |  |  |
| Strategies and Action Steps | Person(s) Responsible | Resources | Timelines | Evidence of Implementation | Evidence of Impact | Formative/ Summative | Title I Schoolwide Components |
| ARD committee will ensure LRE. Staff in-service will be used to define procedural guidelines for referral process and LRE assurance | Victrinia Johnson Diagnostician | Sp.Ed. Law materials | Aug 2024 | In-service agenda | Student schedules and progress reports | F=Staff Dev. S=compare % of referrals and placement | 2 9 |
| Inclusion will be used to the maximum extent as appropriate for LRE | Michael Warren Victrinia Johnson Staff | Sp.Ed. Funds Teachers Diagnostician | Aug 2024-May 2025 | Student schedules | Progress reports | F=Teacher input in ARDS S=EOY ARDs | 2 9 |
| TISD will provide a range of related services (AT,OT,PT, etc.) | Michael Warren Contracted Services | Contracted Services Personnel | Aug 2024-May 2025 | Documented services | Progress reports | F=IEP S=Service Placements | 2 9 |
| TISD will maintain consistent communication with parents and Coop. with regard to re-evaluation timelines, IEP and modification needs. | Matt Mizell Michael Warren Victrinia Johnson Diagnostician | Staff Dev. Phone, email, ARD documents | Aug 2024-May 2025 On-going ARDs | Phone logs ARD documents | EOY ARD documents | F=Letters S=Surveys/Meetings | 2 6 9 |
| TISD will participate in college/ career fairs and post-secondary meetings. | Michael Warren Kaylee Sims Victrinia Johnson | St.Services Budget Diagnostician State Allotments | Aug 2024-May 2025 | Attendance rosters Sign-ins | Post-secondary tracking results | F=Attendance Sign-in S=Student Tracking | 10 |
| Classrooms are monitored on a regular basis by administration | Michael Warren | DMAC/T-TESS | Aug 2024-May 2025 | Walkthroughs | T-TESS results | F=Walkthrough Documents S=T-TESS eval. | 4 |

| Ideal State: Goal(s) Goal 1 Trinidad’s PLC will increase student performance on all academic standards. |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objective(s) Value 3 Administrators will stay current on educational research and issues, and the financing of education will be adequate, equitable, and efficient. |  |  |  |  |  |  |  |
| Strategies and Action Steps | Person(s) Responsible | Resources | Timelines | Evidence of Implementation | Evidence of Impact | Formative/ Summative | Title I Schoolwide Components |
| Administrators will maintain current knowledge of public education policies, programs and best practices, and share knowledge with stakeholders. | Matt Mizell Michael Warren | Admin. Budgets, ESCs, websites, periodicals, Pro. Dev. | July 2024–June 2025 | Pro. Dev. Sign-in and certificates | Turnaround development or staff sharing sessions | F=Attendance S=Documented Training | 4 |
| Monthly financial reports will be sent to the board of trustees. | Matthew Mizell Daniela Sanders | None | Sept. 2024 –Aug. 2025 | Board agenda | Audit report | F=Monthly Reports S=Annual Audit | 1 |
| All purchases and authorization to purchase will go through the Superintendent’s Office. (Need/cost prioritization) | Matt Mizell Michael Warren | None | Sept. 2024-Aug. 2025 | Purchase order documents | Needs assessment decisions | F=Purchase Orders S=Budget Summaries | 1 |

| Ideal State: Goal(s) Goal 1 Trinidad’s PLC will increase student performance on all academic standards. |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objective(s) Value 3 Administrators will stay current on educational research and issues, and the financing of education will be adequate, equitable, and efficient. |  |  |  |  |  |  |  |
| Strategies and Action Steps | Person(s) Responsible | Resources | Timelines | Evidence of Implementation | Evidence of Impact | Formative/ Summative | Title I Schoolwide Components |
| Administrators, teachers, and auxiliary staff will review purchasing procedures and guidelines. | Matthew Mizell Daniels Sanders Micheal Warren | None | Sept. 2024-Aug. 2025 | In-service agenda | Needs assessment decisions | F=Attendance Rosters S=Budget expenditures | 1 |
| All federal funded programs will be evaluated at the end of the year. | Matt Mizell Michael Warren | None | Completed by July 1, 2025 | Meeting agenda | Needs assessment decisions | F=Evaluation Reports S=Annual Evaluation | 1 |
| All fixed costs will be evaluated to determine best value and needs of the districts. | Daniela Sanders Matt Mizell Michael Warren | None | Completed by July 1, 2025 | Meeting | Needs assessment decisions | F=Bids/RFP S=Selections | 1 |
| Grant opportunities will be explored throughout the year. | Josh Polk Natalie Martin Michael Warren Matt Mizell | None | Sept. 2024-Aug. 2025 | Grant applications | Secured grants | F=List of grants reviewed S= # of grants awarded | 1 |

| Ideal State: Goal(s) Goal 1 Trinidad’s PLC will increase student performance on all academic standards. |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objective(s) Value 4 Instructional Strategies will include differentiated instruction and cross-curricular instruction. |  |  |  |  |  |  |  |
| Strategies and Action Steps | Person(s) Responsible | Resources | Timelines | Evidence of Implementation | Evidence of Impact | Formative/ Summative | Title I Schoolwide Components |
| Professional development will be expected and supported in differentiated and cross-curricular instruction. | Kaylee Sims Laci Mizell Michael Warren | Pro. Dev. ESC7 | Aug. 2024-Aug. 2025 | Alignment documents | TEKS mastery progression | F/S= Participation in professional development | 4 8 |
| Teachers will provide evidence of cross-curricular and differentiated instruction. | Instructional Staff | NA | All Year | Lesson Plans | T-TESS | F/S=Lesson Plans, Evaluation Documents | 2 |
| Hands-on targeted Texas Assessment training will be implemented with regard to state and local assessment. | Matt Mizell Michael Warren Core Teachers | General Fund Grants ESC7 | Sept. 2024-Aug. 2025 | Training agenda and attendance | Monitored use of DMAC | F=Participation in Training – Sign-in S=Documented use of DMAC, Lesson Plans | 1 4 7 8 |
| Utilization of summer camps and activities if funds are available. | Matt Mizell Michael Warren Kaylee Sims Staff | General Fund ESSA Funds Carryover Funds | Summer of 2025 | Time Sheets Flyers Social Media Postings | Engagement through percentages of students present | S= Camp Success Survey for Parents, Students and Teachers | 2 |
| Offering more cross-curricular programs for students during the instructional day that will help with correlating academic needs through physical movement. Ex. Gymnastics/Dance | Matt Mizell Michael Warren Kaylee Sims Kevin Fitzgerald | General Fund ESSA/TITLE I Funds | August 2024-July 2025 | Flyers Social Media Postings | Engagement through percentages of students present and participating | S=Documented Lesson Plans, Walk throughs Observations Surveys for program success | 2 |

| Ideal State: Goal(s) Goal 1 Trinidad’s PLC will increase student performance on all academic standards. |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objective(s) Value 5 We will model and expect high quality work, high attendance, and will attract and retain effective staff. |  |  |  |  |  |  |  |
| Strategies and Action Steps | Person(s) Responsible | Resources | Timelines | Evidence of Implementation | Evidence of Impact | Formative/ Summative | Title I Schoolwide Components |
| Teachers will be provided with district approved staff development. | Matt Mizell Michael Warren Instructional Staff | Pro. Dev. ESC7 | Aug. 2024-Aug. 2025 | Pro. Dev. attendance | Document matching development to needs assessment | F=Attendance Rosters S=Annual Evaluation | 1 4 |
| Staff will be trained in the use of computer equipment and software necessary to effectively use with students. | Michael Warren Joshua Polk | Technology Budget | Aug. 2024-Aug. 2025 | Pro. Dev. attendance | Documented use of provided technology | F=Classroom observations S=Skill level assessments | 2 4 |
| TISD will assess the students’ ability to apply technology skills. | Joshua Polk Instructional Staff | None | Completed by May 2025 | Assessment document | Assessment results | F=Assessment instruments S=Skill level assessments | 8 |
| The technology plan will be revised and implemented. | Matt Mizell Michael Warren Josh Polk | None | State timeline | Completed document | Needs assessment decisions | F=Committee Minutes S=Revised plan | 1 2 |
| TISD will offer a longevity stipend. | Matt Mizell | General Fund | Dec. 2024 | Paid Checks | Staff retention | S=Staff Turnover survey | 5 |
| Staff will communicate rubrics, timelines, procedures etc. to students and parents. | Michael Warren Instructional Staff | Letters Website | Sept. 2024 | Documents | Level of parental involvement | F/S=Teacher Documents | 6 |

| Ideal State: Goal(s) Goal 1 Trinidad’s PLC will increase student performance on all academic standards. |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objective(s) Value 5 We will model and expect high quality work, high attendance, and will attract and retain effective staff. |  |  |  |  |  |  |  |
| Strategies and Action Steps | Person(s) Responsible | Resources | Timelines | Evidence of Implementation | Evidence of Impact | Formative/ Summative | Title I Schoolwide Components |
| Attendance committee will develop strategies to achieve 97% ADA for the student population. | Michael Warren Lauren Thompson Kaylee Sims | Henderson County JP | Aug. 2024-May 2025 | Attendance committee meetings Documented strategies | Attendance rates | F=Documented strategies S=PEIMS report | 2 |
| School personnel will verify student absences and encourage good attendance through celebration, recognition, programs and awards. | Michael Warren Lauren Thompson Office Staff | General Fund Ascender ESSA Funds | Aug. 2024-May 2025 | Call logs and Ascender documents | Attendance rates | F=Contact logs S=Monthly reports | 2 |
| TISD will develop rewards for staff and student attendance. | SBDM ESSA Funds | ESSA Funds | Aug. 2024-May 2025 | Documented rewards | Attendance rates | F=Documented incentives | 2 |
| Students and parents will sign the receipt of the TISD handbook which includes the attendance policy. | Michael Warren Lauren Thompson | None | Sept. 2024 As they enroll. | Handbook signing | Parental acknowledgement of policy | F/S=Returned forms | 2 6 |
| TISD will post all openings with specific criteria of interest. | Matt Mizell Kaylee Sims | Professional Organizations | As openings occur | Posted openings | Rate and quality of applicants | F=Notices S=Interview and hiring documents | 5 |

| Ideal State: Goal(s) Goal 1 Trinidad’s PLC will increase student performance on all academic standards. |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objective(s) Value 6 We will implement challenging student-centered activities and instruction. |  |  |  |  |  |  |  |
| Strategies and Action Steps | Person(s) Responsible | Resources | Timelines | Evidence of Implementation | Evidence of Impact | Formative/ Summative | Title I Schoolwide Components |
| Administrators will review lesson plans and offer reflections. | Michael Warren Kaylee Sims | None | Weekly | Walkthrough and T-TESS reflection | Lesson Plans that follow vertical and horizontal alignments | F=Documented walkthroughs S=T-TESS Evaluations | 2 4 |
| Instructional materials will be reviewed for quality. Adjustments and additions will made to ensure students receive rigorous curriculum/instructional strategies to aide in state assessment and post-secondary success. | Matthew Mizell Michael Warren Kaylee Sims | General Fund | October 2024 | Meeting documentation | Student progression of TEKS mastery | F/S=Acquired resources | 1 8 |
| Computer software will be implemented in grades k-12 to enhance TEKS mastery in core subjects. | Instructional Staff | Grant Allotments | Aug. 2024-May 2025 | Log data | Improvement in TEKS mastery | F=Participation S=Assessment Reports | 4 8 |

| Ideal State: Goal(s) ### Goal 2: Trinidad’s PLC will create and maintain a positive learning environment. |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objective(s) Value 7 We will use effective classroom management to create a positive learning environment. |  |  |  |  |  |  |  |
| Strategies and Action Steps | Person(s) Responsible | Resources | Timelines | Evidence of Implementation | Evidence of Impact | Formative/ Summative | Title I Schoolwide Components |
| Level one offenses will be handled and documented by staff. | All staff members | None | Aug. 2024-May 2025 | Referral documents | Relationship building with students - T-TESS | F/S=List of level one offenses handled through office | 10 |
| Level II and above offenses will be referred to administration. | Michael Warren Kaylee Sims | Ascender | Aug. 2024-May 2025 | Referral documents | Documented deterrence | F=List of level II and III offenses handled S=Staff Reports | 10 |
| A system for dealing with referrals during the absence of primary administrators will be implemented. | Michael Warren Kaylee Sims | Designated Staff | Aug. 2024-May 2025 | Listed administrative duties | Timely disciplinary decisions | F=Reports and observation S= Ascender documentation | 10 |
| Discipline documentation will be completed in Ascender in a timely manner for tracking purposes. Necessary staff reports will be generated and shared. | Michael Warren Kaylee Sims | Memos, emails, conferences | Aug. 2024-May 2025 | Ascender data | Use in tracking discipline levels | F=Monthly report S=Survey | 10 |

| Ideal State: Goal(s) ### Goal 2: Trinidad’s PLC will create and maintain a positive learning environment. |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objective(s) Value 7 We will use effective classroom management to create a positive learning environment. |  |  |  |  |  |  |  |
| Strategies and Action Steps | Person(s) Responsible | Resources | Timelines | Evidence of Implementation | Evidence of Impact | Formative/ Summative | Title I Schoolwide Components |
| Good behavior will be acknowledged. | All staff members | Principal’s Budget ESSA Funds | Aug. 2024-May 2025 | Student of Sem. And year | Documented improved campus discipline | F/S=Documented proof of recognition | 10 |
| Safe and drug free programs will be used to promote healthy living. | Michael Warren Marie Bannister | St. Service Budget SSA with ESC7 Title Funds | Aug. 2024-May 2025 | Assemblies Productions | Participant testimony through feedback | F/S=Attendance, lifestyle surveys, drug free program participation | 10 |
| ISS and DAEP will be used to maintain an appropriate academic setting. Placements will be made on an individual basis when other efforts have been ineffective or consequence is mandatory. | Michael Warren Kaylee Sims | General Fund | Aug. 2024-May 2025 | Documented occurrences | Documented deterrence | F=Discipline referrals S=PEIMS 425 record | 10 |

| Ideal State: Goal(s) Goal 3: Trinidad’s PLC will improve communication with all district stakeholders. |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objective(s) Value 8 We will encourage parent and community participation in creating a shared learning experience. |  |  |  |  |  |  |  |
| Strategies and Action Steps | Person(s) Responsible | Resources | Timelines | Evidence of Implementation | Evidence of Impact | Formative/ Summative | Title I Schoolwide Components |
| A campus calendar of events will be made available to the staff and upcoming events will be made public. Staff will be trained in use of Google Calendar. | Michael Warren Office Staff | Newsletters, website, mail, postings, etc. General Fund | Monthly | Calendar completion | Decreased scheduling conflicts | F/S=Weekly calendars and public documents | 1 |
| Trojan Pride will be the link between TISD staff and district stakeholders. Parent volunteers will be encouraged. Parental Meetings. | Michael Warren Trojan Pride | None ESSA Grant | Aug. 2024-May 2025 | Documented events and meetings | Increased parental involvement | F=Membership Roster S=List of event sponsorships | 6 |

| Ideal State: Goal(s) Goal 3: Trinidad’s PLC will improve communication with all district stakeholders. |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objective(s) Value 9 We will encourage parent and community participation in creating a shared learning experience. |  |  |  |  |  |  |  |
| Strategies and Action Steps | Person(s) Responsible | Resources | Timelines | Evidence of Implementation | Evidence of Impact | Formative/ Summative | Title I Schoolwide Components |
| TISD will utilize newspaper media for positive exposure. | Matt Mizell Michael Warren Laci Mizell | General Fund County media | Aug. 2024-May 2025 | Documented listings | Stakeholder dialogue, and enrollment | F/S= # of district articles | 6 |
| Progress reports will be given to every student. | Office Staff | General Fund | Each 3 weeks | Progress reports | Parental knowledge of student progress | F=Individual reports S=Report card grades | 2 6 9 |
| District personnel e-mail addresses, voice mail, and conferences times will be made available to stakeholders. | Matt Mizell Michael Warren Josh Polk | None | Sept. 2024 | Documented availability | Communication logs | F/S=Completed contact information | 6 |
| Site-base team will have scheduled meetings | Administration and Site-base | General Fund | All Year | Meeting agendas and sign-ins | Updated DIP/CIP and needs assessment | F=Meeting Agendas S=Documented activities | 1 2 9 |